## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2211-swen-261-01-d-thePurpleNarwhals
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | MT 10/6/21
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | MT 10/6/21
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | MA, RT, ST 11/10/2021
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | MT 10/6/21
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | MT 10/6/21
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MT 10/6/21
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MT 10/6/21
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MT 10/6/21 |  | MT
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MT 10/6/21 |  | MT
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MA, RT, ST 11/10/2021 |  | MT
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Fail | MT 11/16/21 : This now fails due to multiple games. The user will have to click on the game manually to enter. |  | MT
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MA, RT, ST 11/10/2021 |  | MT
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MA, RT, ST 11/10/2021 |  | MT
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MA, RT, ST 11/10/2021 |  | MT
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MA, RT, ST 11/10/2021 |  | MT
As a Player, I want to confirm my move so I can end my turn and have the opponent move | Given I am in a game when I move a piece to a valid square, then I want a way to confirm my move. | Pass | MA, RT, ST 11/10/2021
| Given That I have made a legal move, my piece should be placed on the spot where I moved to | Pass | MA, RT, ST 11/10/2021
| Given that I have made a legal move, when I have confirmed my move, my opponent should see the move I made | Pass | MA, RT, ST 11/10/2021
As a Player, I want to capture a single checker to remove an opponents piece | Given that it is my turn, when I complete a legal move that would capture a piece, then the opponents piece is captured. | Pass | MA, RT, ST 11/10/2021
| Given that it is my opponents turn, if my opponent captures one of my pieces, my piece gets removed from the board | Pass | MA, RT, ST 11/10/2021
| Given that a piece is removed from the board, when somebody wants to move a piece, the spot that the captured piece was occupying is now an available spot. | Pass | MA, RT, ST 11/10/2021
| Given that I have just captured one of my opponents checkers, when I want to see how many pieces I have captured, it is displayed. | Pass | MA, RT, ST 11/10/2021
As a Player, I want to forfiet at any point so I can end the game | Given that I'm in a game, when I'm making my move, then I must see an option to forfeit the match. | Pass | MA, RT, ST 11/10/2021
| Given that I am in the turn-state (Making a turn) I am unable to resign | Pass | MA, RT, ST 11/10/2021
| Given that I moved a piece, when I click backup to undo my move, the resign button is re-enabled. | Pass | MT 11/16/21
| Given that I'm in a game, when I click the forfeit button, then I expect the be taken to the home page for another game. | Pass | MT 11/16/21
| Given that I pressed the forfeit button, when I check my home page, then I should be able to play another game. | Pass | MT 11/16/21
As a Player, I want to sign out so I can stop playing checkers | Given I am at the home page when I am signed in then I expect a way to sign out | Pass | MT 11/16/21
| Given I am in a game when I am signed in, then I expect a way to sign out | Pass | MT 11/16/21
| Given I am in a game when I sign out, then the game will end and the opponent will win. | Pass | MT 11/16/21
| Given that I sign out when I am signed in, then I expect to be taken back to the home page | Pass | MT 11/16/21
| Given that I am signed in and at the home page, when someone signs out, then their name should be removed from the player list. | Pass | MT 11/16/21
| Given that I am in a game when my opponent signs out, then I expect the game to end and I win the game. | Pass | MT 11/16/21
As a Player, I want to leave a game so I can do other things until my opponent makes a move | Given I want to go to the home page when I am in a game, I want a way to go back to the home page | Pass | MT 11/16/21
| Given I go back to the home page after leaving a game, I want to see the list of players along with the games I'm in. | Pass | MT 11/16/21
| Given I am in a game (or multiple), when I am back at the home menu, then I expect to get back into a game I am in | Pass | MT 11/16/21
As a Player, I want to join multiple games so I can play against more than one person at a time | Given I'm player that currently in a game, when I go to home and click on another game then I expected to be put in another game | Pass | MT 11/16/21
| Given I'm a player in multiple games when I click on a specific player's game then I expected to put into that specific game | Pass | MT 11/16/21
| Given I'm a player in multiple games when I click the home button then I should see all current games I'm in | Pass | MT 11/16/21
As a player, I want to be given a hint that contains a possible move for me to make in case I am stuck. | Given that I am in a game, when it is my turn, I want to have a way to get a hint. | Pass | MT 11/14/2021
| Given that I have asked for a hint, when I am stuck, then I expect a suggestion for a move. | Pass | MT 11/16/21